## Gantt Chart
				WORK WEEK
TaskID	Prereq's	Task name	08/10/12	15/10/12	22/10/12	29/10/12	05/11/12	12/11/12	19/12/12	26/11/12	03/12/12	10/12/12	17/12/12	24/12/12	31/12/12	07/01/13	14/01/13	21/01/13	28/01/13	01/02/13	04/02/13	11/02/13	18/02/13
SE_07_PM_01		Arrange project team positions & investigate project
SE_07_DS_01		Introduction & details of proposed system
SE_07_DS_02		Use Case design documentation
SE_07_DS_03		User interface design documentation
SE_07_PM_02		Gantt Chart/ project plan
SE_07_DS_03		Risk Analysis
SE_07_DEL_01		Project Plan to be delivered
SE_07_DS_04		Diagrams (Class and Component)
SE_07_TEST_01		Identify tests for the final system
SE_07_GM_01		Meeting with other groups to discuss standards
SE_07_TEST_02		Create test specification for final system
SE_07_PM_04		Identify coding tasks and delegate work to group members
SE_07_CODE_01		Skeleton code for project (packages, classes)
SE_07_GM_02		Meeting with other groups to discuss standards
SE_07_DEL_02		Test specification for final system
SE_07_DS_05		Introduction and architectural description
SE_07_DS_06		Interface description and detailed design
SE_07_CODE_02		Coding starts (to be expanded)

SE_07_DS_07		References and appendices
SE_07_GM_03		Meeting with other groups to discuss standards
SE_07_DEL_03		Design specification for final system
SE_07_GM_04		Meeting with other groups to discuss standards
SE_07_DEL_04		Prototype demo #1 and submission to BB
SE_07_DEL_05		Integration and testing week
SE_07_DEL_06		Delivery of software to client
SE_07_DEL_07		Delivery of final documentation

	Legend
	Entire team
	Miles
	Nathan
	Deliverable
	Team A
	Team B
	Group meeting